## bugs
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2025-02-19 | Everyone | P3 | resolved | Chinmay | Bad ship-island collision bounce-back | Ship should bounce back depending on the side of the island it collides with | Ship goes back in opposite direction for every collision | Drive ship into an island with diagonal velocity
2 | 2025-02-19 | Lily | P5 | open | Lily | When pressing up then left then release up for ship movement | should still go left as it's not yet released | it stops going left | go at the ship control station, press space to control ship, then press up then left then release up for ship movement
3 | 2025-02-19 | Brian | P5 | resolved | Lily | Ship still moves when we hold any movement key and unstation. | Ship should stop or slowly stop when we unstation. | It keeps on going at the same speed. | When stationing a ship, press A/D and then press space to unstation while ship is moving.
4 | 2025-02-20 | Clare | P3 | resolved | Clare | bunny does not get saved to the ship | once bunny is not jailed, bunny should move across the screen to board ship | bunny is moving to a specific x y coordinate on the window screen | use weapon to shoot at bunny jail to trigger bunny saving
5 | 2025-02-20 | Clare | P3 | resolved | Brian | enemy does not collide with ship | enemy should collide with ship and take damage | enemy keep moving to the centre of the ship | wait for the spawned enemy to approach the ship
6 | 2025-02-21 | Everyone | P3 | resolved | Brian | Ship collision with island is broken. | We expect the ship to NOT get inside an island | The ship somehow enters the Island | Keep pushing into the island.
7 | 2025-02-22 | Dayshaun | P5 | open | Dayshaun | hitbox of islands isn't aligned with the textures | ship should stop moving when it hits the texture boundary | the island hitboxes extend slightly beyond the textures in areas | drive ship into edge of island and observe closely
8 | 2025-02-22 | Dayshaun | P3 | resolved | Dayshaun | player ship spawns in a fixed location (which could be inside an island) | ship should spawn where the spawnpoint is on the map | ship spawns at a fixed spot regardless of the map | start the game and observe spawning location, compare to where the player spawnpoint is on the map
9 | 2025-02-22 | Dayshaun | P0 | resolved | Brian | program crashes when the game is closed | game should prompt pressing a key to close console when the game window is closed | an exception is thrown and program stops | start the game, and then close the game window or press ESC
10 | 2025-02-22 | Everyone | P0 | resolved | Brian | program crashes when pressing R to restart | Should not crash, R should not do anything in our game | should not crash and should not do anything | just press R after starting the game
11 | 2025-02-22 | Chinmay | P5 | open | Lily | Ship stops immidiately in one direction of the two | Ship should slowly stop in either direction after releasing key | ship stops in the one direction when one of the two keys is released | Move the ship diagonally and release one of the keys
12 | 2025-02-22 | Dayshaun/Clare | P5 | open | Lily | diagonal movement is faster | should go same speed in every direction | going in diagonal is faster | compare speed of holding A to holding both W and A
13 | 2025-02-22 | Brian | P4 | open | Brian | The interactivity of a UI isn't accurate (pixel perfect) with the textures.Not all UI have appropriate offset. | When hovering/interacting with UI elements it should be accurate. | You can interact if it's a few pixel off. Or even a transparent texture. | The UI can be interacted (click, hover, etc.) if it's a few pixel of the "visible" texture.

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release